## BLANK ONE SPOR Chart & Burndown
SCRUM PROJECT MANAGEMENT ONE SPORT CHART
ONE SPORT CHART AND BURNDOWN
[9 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
1 | Setup of the environment |  | 60 | 60 | 120 |  |  |  | 12 | 100%
1.1 | Database postgres | Marco | 10 | 10 | 0 | 1 | 2024-05-06 | 2024-05-07 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T
1.2 | Backend models | Valerio | 10 | 10 | 0 | 1 | 2024-05-06 | 2024-05-07 | 2 | 100% | bar: WEEK 1 M to WEEK 1 T
1.3 | Configuration db/backend | Marco | 15 | 15 | 0 | 1 | 2024-05-08 | 2024-05-10 | 3 | 100% | bar: WEEK 1 W to WEEK 2 F
1.4 | Routes definition | Valerio | 15 | 15 | 0 | 1 | 2024-05-13 | 2024-05-15 | 3 | 100%
1.5 | Creation of Angular project | Valerio | 10 | 10 | 0 | 1 | 2024-05-16 | 2024-05-17 | 2 | 100%
2 | Backend development |  | 50 | 50 | 100 |  |  |  | 11 | 100%
2.1 | Authentication route | Marco | 10 | 10 | 0 | 2 | 2024-05-20 | 2024-05-21 | 2 | 100% | bar: WEEK 2 M to WEEK 3 T
2.2 | Order route | Marco | 10 | 10 | 0 | 2 | 2024-05-22 | 2024-05-23 | 2 | 100% | bar: WEEK 3 W to WEEK 3 T
2.3 | Cart route | Valerio | 10 | 10 | 0 | 2 | 2024-05-23 | 2024-05-24 | 2 | 100% | bar: WEEK 3 T to WEEK 3 F
2.4 | Products route | Valerio | 15 | 15 | 0 | 2 | 2024-05-27 | 2024-05-29 | 3 | 100% | bar: WEEK 4 M to WEEK 4 W
2.5 | Dockerfile backend | Marco | 5 | 5 | 0 | 2 | 2024-05-30 | 2024-05-31 | 2 | 100% | bar: WEEK 4 T to WEEK 5 F
3 | Frontend development |  | 65 | 65 | 130 |  |  |  | 18 | 100%
3.1 | Creation of the components | Marco | 5 | 5 | 0 | 3 | 2024-06-03 | 2024-06-05 | 3 | 100%
3.2 | Add service API | Valerio | 10 | 10 | 0 | 3 | 2024-06-05 | 2024-06-06 | 2 | 100%
3.3 | Add authentication API | Valerio | 10 | 10 | 0 | 3 | 2024-06-06 | 2024-06-07 | 2 | 100%
3.4 | Details page | Marco | 10 | 10 | 0 | 3 | 2024-06-10 | 2024-06-11 | 2 | 100% | bar: WEEK 5 M to WEEK 6 T
3.5 | Cart page | Marco | 10 | 10 | 0 | 3 | 2024-06-12 | 2024-06-14 | 3 | 100% | bar: WEEK 6 W to WEEK 6 F
3.6 | Confirm order page | Valerio | 10 | 10 | 0 | 3 | 2024-06-17 | 2024-06-18 | 2 | 100% | bar: WEEK 7 M to WEEK 7 T
3.7 | User's order page | Marco | 5 | 5 | 0 | 3 | 2024-06-19 | 2024-06-20 | 2 | 100% | bar: WEEK 7 W to WEEK 7 T
3.8 | Dockerfile frontend | Valerio | 5 | 5 | 0 | 3 | 2024-06-20 | 2024-06-21 | 2 | 100% | bar: WEEK 7 T to WEEK 8 F
4 | Finalization of functionalities and testing |  | 38 | 38 | 76 |  |  |  | 11 | 100%
4.1 | Testing of Authentication API | Valerio | 10 | 10 | 0 | 4 | 2024-07-08 | 2024-07-10 | 3 | 100% | bar: WEEK 10 M to WEEK 10 W
4.2 | Testing of service API | Marco | 10 | 10 | 0 | 4 | 2024-07-10 | 2024-07-12 | 3 | 100% | bar: WEEK 10 W to WEEK 11 F
4.3 | Creation of docker-compose | Valerio | 10 | 10 | 0 | 4 | 2024-07-15 | 2024-07-16 | 2 | 100%
4.4 | Testing final product | Marco | 8 | 8 | 0 | 4 | 2024-07-17 | 2024-07-19 | 3 | 100%
|  |  | ESTIMATE | COMPLETED | REMAINING | DAYS worked in total (if we worked the same day we count it as 1 day) | EST/DAYS
| BURNDOWN DATA | TOTAL HOURS | 749 | 749 | 230 | 66 | 11.3485 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | [10 empty] | TOTAL HOURS
[6 empty] | ^ Enter number of days |  |  |  | PLAN | 749 | 749 | 749 | 749 | 737.6515 | 726.303 | 714.9545 | 703.6061 | 692.2576 | 680.9091 | 669.5606 | 658.2121 | 646.8636 | 635.5152 | 624.1667 | 612.8182 | 601.4697 | 590.1212 | 578.7727 | 567.4242 | 556.0758 | 544.7273 | 533.3788 | 522.0303 | 510.6818 | 499.3333 | 487.9848 | 476.6364 | 465.2879 | 453.9394 | 442.5909 | 431.2424 | 419.8939 | 408.5455 | 397.197 | 385.8485 | 374.5 | 363.1515 | 351.803 | 340.4545 | 329.1061 | 317.7576 | 306.4091 | 295.0606 | 283.7121 | 272.3636 | 261.0152 | 249.6667 | 238.3182 | 226.9697
[10 empty] | ESTIMATE | 749 | 746 | 743 | 749 | 744 | 739 | 736 | 733 | 730 | 724 | 721 | 717 | 711 | 704 | 699 | 694 | 689 | 684 | 679 | 676 | 673 | 670 | 666 | 663 | 659 | 655 | 652 | 649 | 646 | 643 | 640 | 636 | 632 | 628 | 624 | 616 | 609 | 605 | 601 | 597 | 594 | 594 | 594 | 594 | 594 | 594 | 594 | 594 | 594 | 594 | [10 empty] | 30833
[9 empty] | Enter hours completed per day ----> | HRS COMPLETED | 3 | 3 | 3 | 5 | 5 | 3 | 3 | 3 | 6 | 3 | 4 | 6 | 7 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 4 | 3 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 4 | 8 | 7 | 4 | 4 | 4 | 3 | [20 empty] | 155
[10 empty] | HRS REMAINING | 746 | 743 | 740 | 744 | 739 | 736 | 733 | 730 | 724 | 721 | 717 | 711 | 704 | 699 | 694 | 689 | 684 | 679 | 676 | 673 | 670 | 666 | 663 | 659 | 655 | 652 | 649 | 646 | 643 | 640 | 636 | 632 | 628 | 624 | 616 | 609 | 605 | 601 | 597 | 594 | 594 | 594 | 594 | 594 | 594 | 594 | 594 | 594 | 594 | 594 | [10 empty] | 30678
CLICK HERE TO CREATE SCRUM PROJECT MANAGEMENT GANTT CHART TEMPLATES IN SMARTSHEET

## Release Backlog
SCRUM PROJECT MANAGEMENT ONE SPORT CHART
RELEASE BACKLOG
PRIORITY | SPRINT | FUNCTIONALITY | TASK TITLE | TASK DESCRIPTION | TASK OWNER | WORK ESTIMATE IN HOURS | STATUS | NOTES | STATUS KEY | WORK ESTIMATE IN HOURS
High | 1 | Having the whole environment ready | Setup of the Environment | In this sprint our objective was to have all the basics structure implemented |  | 40 | Completed |  | Not Started | 1
High | 2 | Implementing the backend functionalities | Backend Development | We exclusively focused on the backend, testing all the routes |  | 40 | Completed |  | In Progress | 2
High | 3 | Implementing the frontend functionalities | Frontend Development | We utilized Angular to create the Frontend pages and all components, and we also added the necessary external API to backend features. |  | 80 | Completed |  | Completed | 4
Medium | 4 | Finalization of the system | Finalization and testing | Execution of the final features |  | 40 | Completed |  |  | 8
16
24
40
80